## 2025
Datum |  | Stunden | AbrZyklus
2025-05-20 | Review // SpM26: Final test + Livesetzung Prod // Process Val2Phr | 4 | 202506
2025-05-21 | SpM27: Further investigation // New Process: Setting up Holger | 6 | 202506
2025-05-22 | Alignment Michael + Alice regarding SpM26 // New Process: Process-Chart | 5 | 202506
2025-05-23 | Align Nicolai wegen Umrechnung Units // New Process: Redesign | 3 | 202506
202506
2025-05-26 | Align Alice // Meeting Thomas wg. New-Process // EHS-SQL weekl | 4 | 202506
2025-05-27 | Review-Meeting // New Process: Load Vals in Phrase-Tabs: Creating Rules | 5 | 202506
2025-05-28 | Standup // Meet Holger wg. Test new Process // Problem-Solving CABN+CAWN | 6 | 202506
202506
2025-06-02 | Stand-Up mit Alice // Copy new Master-Data for Mapper // Alignn Lidia + Peter // Review-Meeting | 4 | 202506
2025-06-03 | Report Comp-Unit // Align Alice for Extension of SpM20 | 6 | 202506
2025-06-04 | Create draft of SpM20 // Meet Holger | 4 | 202506
2025-06-05 | Change of Extension of SpM20: Rework design // Problems with mapper // enviDataReview | 5 | 202506
2025-06-06 | Stand-Up with align about various Special-Mappings // New version of SpM20 to production | 3 | 202506
2025-06-11 | Stand-Up with new Errors UAT // Re-Work new Process Val2Phrase // Meet Holger | 6 | 202506
2025-06-12 | New Requirements SpM25 // Align Alice // enviDataReview | 5 | 202506
2025-06-13 | ^^ | 8 | 202506
2025-06-16 |  | 7 | 202506 | 81
2025-06-17 | Review + Setup Value 2 Phrase in QA-Mapoper | 5 | 202507
2025-06-18 | Create New RuleSet for Value 2 Phrase | 3 | 202507
2025-06-19 | SpM25 to Prod // Creating rules for Value 2 Phrase | 4 | 202507
2025-06-20 | Align Alice // Draft SpM28 // Preparation Testplan Value2Phrase | 6 | 202507
2025-06-23 | SpM25: Resolving Prod-Errors // Continue Work on SpM28-Draft | 4 | 202507
2025-06-24 | enviData-Review // Meet Lidia // Prep Rules for SpM28 | 5 | 202507
2025-06-30 | Stand-Up: Prep Load Wave 0 --> Extend SubIDs // Meet Lidia | 6 | 202507
2025-07-01 | enviDataReview // Delta-Load Customizing-Mapper | 7 | 202507
2025-07-02 | Stand-Up // Prep Load | 6 | 202507
2025-07-03 | err-Correction IdentUsages + VAIChars // Meet Holger // Review | 5 | 202507
2025-07-04 | Finding Root-Cause for SpM01-error // Quick-Fix // Business Alignment | 5 | 202507
2025-07-07 | Stand-UP: De-Briefing SIT // Align Steffi Welz SpM01 // Fix Error SpM01 | 3 | 202507
2025-07-08 | enviDataReview // Design Test Value2Phrase End2End | 5 | 202507
2025-07-09 | Stand-Up // Prep Test-Case for Value-2-Phrase // Align Alice --> Test-DB | 6 | 202507
2025-07-10 | Set-Up Rules For End2End-Test // Align Alice SpM31 // enviDataReview | 5 | 202507
2025-07-11 | SpM31: Draft // Delta-Mapper-Anpassungen für Alice | 5 | 202507
2025-07-14 | Stand-Up // Meet Lidia // Align Grimmeisen reg. Value2Phrase // Transport SpM31 to Prod | 4 | 202507
2025-07-15 | enviDataReview // Doku Transport Rules // BUG 674357 // Align Alice reg. End2End-Test | 5 | 202507
2025-07-16 | Meet Holger // Re-Create SpM27: Draft // Open-Content-Connector: Recherche | 6 | 202507
2025-07-17 | Meet Holger // Re-Create SpM27: Rules // enviData-Review & Planning | 5 | 202507
2025-07-18 | Agenda Workshop OCC // | 3 | 202507 | 103
2025-07-21 | Stand-up // Fixing error in SpM27 // Meet Lidia // Handover SpM30 Alice | 3 | 202507
2025-07-22 | Error-Fixing SpM31 in prod // Projekt Nugget: Handover from Michael | 6 | 202508
2025-07-23 | Projekt Nugget: Analyzing scripts and data / Creating Task and RuleSets on QA | 7 | 202508
2025-07-24 | Projekt Nugget: Analyzing scripts and data / Creating Task and RuleSets on QA | 8 | 202508
2025-07-25 | Projekt Nugget: Installing views // Fix error on draft | 5 | 202508
2025-07-28 |  | 5 | 202508
2025-07-29 | enviData Review // Abst. Grimmeisen, obwohl krank // Gespräch SW-Kontor // Final Views Nugget | 6 | 202508
2025-07-30 | StandUp Alice // Korrektur Views Nugget // Code-Review Holger // Test SpM27 | 6 | 202508
2025-07-31 |  |  | 202508
2025-08-01 |  |  | 202508
2025-08-04 | Stand-Up Alice // Code-Verwaltung /( SpM-2 | 4 | 202508
2025-08-05 | enviDataReview // SpM27: Bug // Nugget: change Scope // error Source-Data IdentUsages | 6 | 202508
2025-08-06 | Stand-UP // Corrected SpM27 to Prod // Prod-Load // Bug 659746 | 7 | 202508
2025-08-07 | Error-Fixing Christina: Value-Mapping // Meet Holger // Cutover Alice // Review-Meeting | 6 | 202508
2025-08-08 | Nugget: New Requirements Michael | 4 | 202508
2025-08-11 | Stand-Up Alice // Meet Lidia // Finalizing new Nugget-Reports | 5 | 202508
2025-08-12 | enviData-Review // Testing new Nugget-Reports // | 3 | 202508
2025-08-13 | Prep-Meeting Christina Conductivity // SpM31: Code-Review // Meet Lidia | 5 | 202508
2025-08-14 | Meeting Christina Conductivity // Bug 65674 Review // enviDataReview // Meet Peter Schubert | 4 | 202508
2025-08-15 | Projekt Nugget: GoLive-Setzung // Rules for Importing Val2Phrase in Mapping-DB | 2 | 202508 | 89
2025-09-01 | Stand-Up Alice // Handover SpM32 | 3 | 202509
2025-09-02 | enviDataReview // Align Thomas Dann Regarding Server Update // Further Discussions on SpM32 | 4 | 202509
2025-09-03 | Stand-Up Alice // Draft SpM30 // Alginment Alice Regarding SpM30 | 3 | 202509
2025-09-04 | Upload SpM30 Test-Results // Align Alice Regard. SpM30 // Build Rules SpM30 | 4 | 202509
2025-09-05 | IT-Test SpM30 // Orga | 2 | 202509
2025-09-08 | Stand-Up Alice // Aligning SpM30-results | 1 | 202509
2025-09-09 | enviDataReview // Upload SpM30 to Prod | 2 | 202509
2025-09-10 | Stand-Up Alice & Michael // enviDataMapper-problems // Align Michael regard. New Schedule | 2 | 202509
2025-09-11 | SpM30 Error Fixing: New Usages // Test Error-Fixing // Move Adapted Rules 2 Prod | 3 | 202509
2025-09-12 | Projekt Nugget: Anpassung Prod-Rules // Adapt Collation-Conflict Langu-Rules // Align Michael | 4 | 202509
2025-09-15 | Stand-Up Michael // Nugget: Change View // Meet Lidia // Prep Meeting Holger | 4 | 202509
2025-09-16 | enviDataReview // Meet Holger: SpM28 // Tests Delta-Mapper | 5 | 202509 | 37
2025-09-17
2025-09-18
2025-09-19
2025-09-22 | Stand-Up Alice // SW-Kontor Meet // Align Holger SpM28b // Test Delta-Mapper QA | 4 | 202510
2025-09-23 | enviDataReview // Align Michael: QA-Mapper-Test // Rules 28b // | 5 | 202510
2025-09-24 | Stand-Up: Val2Phrase // err ListVal-Mapping // Meet Holger | 7 | 202510
2025-09-25 | New Process: ListVal2ListVal: Loading Destination Tree | 4 | 202510
2025-09-26 | New Process: ListVal2ListVal: Mapping FieldValues | 3 | 202510
2025-09-29 | Stand-Up Alice // Test ListVal2Val // Reviewing DB-Error FieldVal2Val | 5 | 202510
2025-09-30 | Meet Lidia // Meet Holger // Rework Rule 677: Adjust VAINOs | 5 | 202510
2025-10-01 | Support Alice with SQL // Meet Holger & Alice reg. Val2Phrase // Fix VAINo-error | 4 | 202510
2025-10-02 | enviDataReview // Missing DG_CL-Subs | 4 | 202510
2025-10-06 | Stand-Up MG+AdG // Meet Lidia // Meet Holger | 3 | 202510
2025-10-07 | enviDataReview // Source-Code Präse Holger // White-List-Problem Michael. | 5 | 202510
2025-10-08 | Stand-Up // Server-Problem Thomas Dann // Meet Holger SpM28b // Analyse mfd-Tabellen | 5 | 202510
2025-10-09 | Analyse Solution SpM28b // enviData-Review // Tutorial on mfd-Solution | 4 | 202510
2025-10-10 | Reflection on mfd-solution (Michael) // Delete-Script to Rule | 3 | 202510
2025-10-13 | Stand-Up Michael // Meet Lidia // Meet Holger // Test-Run SpM28b | 4 | 202510
2025-10-14 | enviDataReview // Error-Correction SpM28b // Updating Val2Phr-Instances | 3 | 202510
2025-10-15 | Stand-Up // Server-discussion (RAM/CPU) // SpM28b: Meet Holger | 4 | 202510
2025-10-16 | Adust VAINo: Change ruleSet-Orders // enviDataReview // Bug 686262: productive test | 5 | 202510
2025-10-17 | CodeReview SpM28b Holger // Handover SpM28b Michael | 3 | 202510 | 80
2025-10-27 | Urlaub | 0 | 202511
2025-10-28 | Check E-Mails // enviDataReview // Align Thomas + Michael wg. GetTogether | 4 | 202511
2025-10-29 | Stand-Up // Handover SpM32 // Test-Run Std-Mapping // Code-Review SpM28b | 6 | 202511
2025-10-30 | Rework positive list // enviDataReview // Align Errors in SpM28b with Alice | 5 | 202511
2025-10-31 | Draft SpM32 // Align Michael Draft BlackList | 4 | 202511
2025-11-03 | Stand-Up Michael // Meet Lidia // Michael: Report reg. Inheriting Substances | 4 | 202511
2025-11-04 | enviDataReview // Check Michaels Rep // Align Thomas // New draft 28b | 5 | 202511
2025-11-05 | Stand-Up Michael+Alice // new design RuleSets // Rework SpM28b | 4 | 202511
2025-11-06 | SIT SpM28b // enviDataReview // Align SIT Alice | 5 | 202511
2025-11-07 | Extend SpM28b with newly mapped VAIUsages | 4 | 202511
2025-11-10 | Standup // Meet Lydia and Holger // Extend SpM28b with User-Def-Texts | 3 | 202511
2025-11-11 | enviDataReview // 2nd SIT SpM28b // Meet Holger regarding GIT | 5 | 202511
2025-11-12 | enviDataReview // Fixing errors SpM28b // Git Holger + Michael | 5 | 202511
2025-11-13 | SpM32: Rules // SIT SpM32 // enviDataReview | 4 | 202511
2025-11-14 | SpM32: Test und Produktivsetzung // Align Alice SpM28 SpM28b | 4 | 202511
2025-11-17 | Rework SpM28 SpM28b // Meet Lidia + Meet Holger | 4 | 202511
2025-11-18 | Align Alice BlackList // enviDataReview | 4 | 202511 | 70
2025-11-19 | Stand-Up // Align Thomas M. regarding BlackList-SPs | 4 | 202511
2025-11-20 | Develop Black-List SPs // Align Server-Migration with Michael | 4 | 202511
2025-11-21 | Handover BlackList-SPs to Thomas M. // Align Agenda for LU-visit Thomas D. | 4 | 202511
2025-11-24 | Besuch Ludwigshafen: BASF | 8 | 202511
2025-11-25 | Besuch Ludwigshafen: Software-Kontor | 8 | 202511
2025-11-26 | Stand-Up: SpM28b Re-Test // Fixing Problems 28b // Recap visit LU | 4 | 202511
2025-11-27 | Various Attempts 2 Install RedGate // Prep Rules for documentation: Confluence-Template | 5 | 202511
2025-11-28 | SpM28 + SpM28b: Overlapping of VAIs --> Align Alice | 4 | 202511
2025-12-01 | Stand-Up // Align Alice reg. 28 VAIUserDefTexts // Meet Lidia // GIT-Problem Holger | 5 | 202511
2025-12-02 | enviDataReview // Draft BlackList: Integrating in ApplyMapping // exec-Task-Problem: Missing DB-ID | 4 | 202511
2025-12-03 | Stand-Up: DG-Subs: First alignment // DB-Move: decisions about DBs // SpM28 to Prod | 5 | 202511
2025-12-04 | Align Michael reg. DG-Subst. // enviDataReview | 5 | 202511
2025-12-05 | BlackList: Analyzing rules, if relevant + adapting rules | 4 | 202511
2025-12-08 | Stand-Up Michael // BlackList: Integrating rules // new QA-Server: Test-run applyMapping | 5 | 202511
2025-12-09 | enviDataReview // BlackList: IT-Test QA-Server // Draft DG-Mapping | 4 | 202511
2025-12-10 | Stand-Up // Fix Errors BlackList // Continue DG-Mapping | 4 | 202511
2025-12-15 | StandUp: Alice/Thomas reg. BlackList // BlackList to QA-Server // Prep Delta Custom. Mapper | 4 | 202512_2
2025-12-16 | enviDataReview // Delta Custom. Mapper: First Test-Run | 5 | 202512_2
2025-12-17 | StandUp: Alice/Thomas reg. Delta Cust-Mapper // Delta-Mapper: Further test-runs | 4 | 202512_2
2025-12-18 | Align Thomas reg. Cust-Mapper // enviDataReview // Connect new Cust-Mapper to GUI | 5 | 202512_2
2025-12-19 | Correct errors Delta-Cust-Mapper // Align Alice reg. Cust-Mapper | 4 | 202512_2
2026-01-05 | Align Meetings Michael // Orga: Summarize 2025_12 // Meet Lidia | 5 | 202601
2026-01-06 | enviDataReview: Server-Migration (1h) // Check Prod-Server-DBs (2h) // Overwrite UserName-Cols | 6 | 202601
2026-01-07 | SIT Username-Cols // Server-Migration: How2Transport (2h) // | 4 | 202601
2026-01-08 | envidatareview // Delta Customizing-Mapper Draft | 5 | 202601
2026-01-09 | Preparations SIT // Delta Customizing-Mapper // Align Michael reg. SIT | 5 | 202601
2026-01-12 | Stand-Up //Check of BlackList-Rules on Prod // Meet Lidia // Prep Rules for Delta-Cust-Mapper | 5 | 202601
2026-01-13 | enviDataReview // Meeting reg. DG: new Scope // Finalize Delta Customizing-Mapper | 5 | 202601
2026-01-14 | Stand-Up // DG-Tabellen // Customizing-Mapper Source // Install Redgate Patrizia | 6 | 202601
2026-01-15 | Compare-DB: Customizng-Mapper // Align Alice + Michel reg. Cust-Mapper // Quick-Fixes Cust-Mapper | 5 | 202601
2026-01-16 | Cust-Mapper Destination // envidataReview // DG: Align Sonja/Daniela // SIT Customizing-Mapper | 4 | 202601
2026-01-19 | Stand-Up wg. TCG79 // New DG-Approach // enviDataWeekly // Test IMG-Mapper Alice | 4 | 202601
2026-01-20 | enviDataReview // Cust-Mapper-SIT with Alice // Investigate on Customizing-Entries ZD4 | 5 | 202601
2026-01-21 | Stand-Up // Compare DB tool // Align misiing User Defined Texts // Align IMG-Mapper | 4 | 202601
2026-01-22 | Solution Desing Missing UDF // enviDataReview // Align new Requirements Alice | 5 | 202601
2026-01-23 | Re-Design SpM28b + SpM32: Considering new Requirements // Orga | 4 | 202601
2026-01-26 | Stand-Up (1h) // Meet Lidia // Investigate Process UDT // Align Michael reg. Check-Function | 5 | 202602
2026-01-27 | enviDataReview // Meet reg. UserDefTexts // Adjustments CABN-Report: MultiChar | 4 | 202602
2026-01-28 | Stand-Up // Prep Test-Run VAIUserDefTexts // Adjust Std-Mapping-Process: CABN // | 6 | 202602
2026-01-29 | Align Michael reg. VAIUserDefTexts + CharMulti-Error // enviDataReview // VAIUserDefText-Rule | 4 | 202602
2026-01-30 | Review VAIUserDefText-Rule // Handover Alice + Michael | 3 | 202602
2026-02-09 | E-Mail // Stand-Up // Open-Topics-Talk: Michael + Alice // Meet Lidia // | 5 | 202602
2026-02-10 | enviDataReview // Draft Multi-Char in Single // Align Alice + Michael reg. New Rules | 6 | 202602
2026-02-11 | Stand-Up // Creating Task Multi-Char in Sinlge // Analyzing potential error SpM18 | 4 | 202602
2026-02-12 | Align Alice pot. Error SpM18 // Doku Code-Review // enviDataReview | 4 | 202602
2026-02-13 | Code-Review Rule 2800 (Holger) // Align Michael Code-Review + Handover | 3 | 202602
2026-02-16 | Meet Lidia // Copy Rules from QA to Prod // Align Thomas Dann RefSubID-Mapping | 3 | 202602
2026-02-17 | Prep Code-Review Dok // DG-Preparation // Align Thomas Dann reg. DG | 4 | 202602
2026-02-18 | Compare Rules QA and Prod // DG-Rules Setup // Finalize Code-Review Dok | 5 | 202602
2026-02-19 | Align Dann reg. Mapping // Align Alice next Steps // enviDataReview // | 4 | 202602
2026-02-20 | Prepare Rules for GoLive // Align Alice reg. GoLive + DG // Review SpM19 | 5 | 202602
2026-02-23 | Stand-Up // Prep Michael reg. GoLive // Meet Lidia // DG: Preparing Rules // SpM19 to Prod | 6 | 202603
2026-02-24 | enviDataReview // DG: Align Alice // Testing DG | 4 | 202603
2026-02-25 | Stand-Up // Code-Review Holger // Evaluate DG-results | 5 | 202603
2026-02-26 | Transfer DG into Rules // enviDataReview // | 4 | 202603
2026-02-27 | Setup Test-Task and -RuleSet for DG // Preparing Test-Data and SIT for DG | 3 | 202603
2026-03-02 | Stand-Up // Meet Lidia // DG-Finalization // 1st Meeting Extension SpM1 | 5 | 202603
2026-03-03 | enviDataReview // Integrate DG-rules and -paraTab to Prod // Meet Holger and Klaus reg. GIT | 6 | 202603
2026-03-04 | Stand-Up // Importing new parameters in SPM01-table // Align Alice new requirements DG | 5 | 202603
2026-03-05 | Integrating new requirements DG // Align Thomas D. reg. GHS // enviDataReview // Importing paraTab SpM01 | 4 | 202603
2026-03-06 | GoLive Support for Alice (BUG 969784) // Michael: Transfer project Nugget to project Onca | 5 | 202603
2026-03-09 | Stand-Up // Fixing error in Extension SpM01 // Meet Lidia // Klaus kurze Einführung | 4 | 202603
2026-03-10 | enviDataReview // Align ParaTab SpM01 // Extension SpM01 to Prod | 6 | 202603
2026-03-11 | Stand-Up // Meet Holger reg. GIT // Check Customizing-Values with Michael | 5 | 202603
2026-03-12 | Draft Report Missing Customizing Values // enviDataReview // Align DG Alice | 3 | 202603
2026-03-13 | Source-Code-Workshop // Finalizing DG with Alice | 5 | 202603
2026-03-16 | Stand-Up + Weekly// Integrating Logging in DG-Mapping // Prep Workshop for Klaus | 5 | 202603
2026-03-17 | enviDataReview // Another Error-Fix DG // Align Alice reg. DG | 4 | 202603
2026-03-18 | Stand-UP // Prep Rules for DG // Setup Delta-Customizing Mapper UAT | 5 | 202603
2026-03-19 | Prep Doku Customizing-Mapper // Align Th. Dann SpecRef-Mapping //enviDataReview | 6 | 202603
2026-03-20 | Meet Alice + Michael reg. Customizing-Mapper // Integrate DG-Rules in Mapping-Flow | 3 | 202603
2026-03-23 | Stand-Up + Weekly// Prep UAT-Load // Integrate Delta-Customizing Mapper UAT | 5 | 202603
2026-03-24
2026-03-25 | Stand-Up: Align DG-Integration // Multiple Test-runs for UAT-Load // Error Fixing | 5 | 202604
2026-03-26 | Integrate DG-results in SpecRef-Mapping // Change rules-order // enviDataReview | 4 | 202604
2026-03-27 | Orga // Align Alice reg. paraRefSubIDMapping // Meet Lidia reg. Plan for GIT // Analyze nText-problem | 5 | 202604
2026-03-30 | Stand-Up Michael: Plan for Changing Field Def. nText // Draft xChange nText // | 4 | 202604
2026-03-31 | enviDataReview: Integrating nText xChange in Std.-Proz. // Align Michael reg. DG | 5 | 202604
2026-04-01 | Diagramm for Klaus 1st ruleSet // Investigate on single error DG-Values | 3 | 202604
2026-04-02 | enviDataReview // Meet Thomas + Michael reg. GIT | 4 | 202604
Karfreitag
2026-04-07 | Testing DG (again) // enviDataReview (1h) //Align Alice reg. DG-Test // Support Klaus | 3 | 202604
2026-04-08 | Stand-Up // Planning Process with GIT // Process-diagramms for GIT | 5 | 202604
2026-04-09 | Align Alice reg. New Vals for SpM01 // enviDataReview // Discussion reg. GIT | 5 | 202604
2026-04-10 | Meet Klaus reg. GIT-Solution // Transport DG-Rules to Prod / Prep apply-Mapping for Alice | 4 | 202604
2026-04-13 | Stand-Up // Align Patrizia reg. PowerShell // Meet Peter // Investigating enviDataChecks-DB | 4 | 202604
2026-04-14 | Preparing sql-files for GIT // Align Michael reg. GoLive // Patrizia reg. DataCompare QA to Prod | 4 | 202604
2026-04-15 | Meet Klaus + Thomas wg. GIT // enviDataReview // Thomas M. eclipse-GIT // Problems granulometry | 5 | 202604
2026-04-16 | GIT: Compare DB Prod / QA // Alignment Christina Granulometry // | 4 | 202604
2026-04-17 | Extend SpM18: Delete VAIUserDefTexts // Create new Rule for SpM18 // Prep applyMapping SpM18 | 6 | 202604
2026-04-20 | Stand-Up // GoLive-Support // Adjust rules on Prod // Bugfix VAIUserDefTexts | 6 | 202604
2026-04-21 | enviDataReview // Align Patricia reg. GIT-Files // | 4 | 202604
2026-04-22 |  |  | 202604
2026-04-23 |  |  | 202604
2026-04-24 | enviDataLoadFiles Correction // | 5 | 202605
2026-04-27 | Stand-Up // Meet Peter // Reports with Alice // enviDataLoadFiles: Align Thomas Merenyi | 5 | 202605
2026-04-28 | enviDataReview // Tutorial Klaus // Singke-Char-Multi-Char-Report | 4 | 202605
2026-04-29 | Stand-Up Ext // Align Klaus reg. Map_SpecRef // Process-diagramm map_SpecRef | 6 | 202605
2026-04-30 | Align Klaus reg. Rules-Draft // enviDataReview // Prep Rules Klaus' Tutorial | 4 | 202605
2026-05-04 | Stand-Up // Meet Peter // | 3 | 202605
2026-05-05 | enviDataReview // Manual GIT-process //Draft Pipelines: Updating table Rules | 4 | 202605
2026-05-06 | Stand-Up // Align Alice reg. Test nText // GIT: 1st Step Pipelines // Change Rules for nText (1070,1130) | 5 | 202605
2026-05-07 | documentation manual GIT-process // enviDataReview // Align Michael after sick-leave | 5 | 202605
2026-05-08 | Contiue GIT-process // Feser-Report // Align Alice reg. GIT and Checks for applyMapping | 4 | 202605
2026-05-11 | Stand-Up // Visualize GIT-Process // Meet Peter // Bug 988097 // Error Cust-Mapper QA | 5 | 202605
2026-05-12 | enviDataReview // bug 686574 // Error Cust-Mapper Prod // Error vUDT // | 6 | 202605
2026-05-13 | Stand-Up (ext) // Support Michael EC-problem // Alice pre- and post-rules | 4 | 202605
2026-05-18 | Stand-Up // Problem Phrase-Mapper // Meet Lidia // Align Klaus reg. SpecRefs // Align Michael | 5 | 202605
2026-05-19 | enviDataReview // Change Data-Definition: nText 2 VARCHAR(MAX) // Test map-SpecRef | 4 | 202605
2026-05-20 | Stand-Up // Align Alice reg. SpecRef // Continue Tutorial Klaus // Upload csv-File 2 Database | 4 | 202605
2026-05-21 | BUG 990324 // Prep Task 3125 for Prod // enviDataReview // Align Alice reg. DG | 5 | 202606
2026-05-22 | Align Alice reg. DG-problem // Align Klaus reg. New Rules // BUG 715398 | 4 | 202606
2026-05-26 | Adjust Customizing-Mapper-Process to new design // SIT Cust-Mapper-Delta // Check with Alice | 5 | 202606
2026-05-27 | Align Alice reg. Cust-Mapper // Cust-Mapper Rules 2 Prod // DG: Error Fixing | 4 | 202606
2026-05-28 | Prod-Run Cust-Mapper-Delta // Error Fixing Prod-Run Cust-Mapper // Prep Demo new DG | 5 | 202606
2026-05-29 | New DG-process: Test run --> evaluation | 3 | 202606
2026-06-01 | Stand-Up // Re-organising eDM-Cust // Prep presentation for new DG-process | 5 | 202606
2026-06-02 | envDataReview // Align new DG-process // Install new DG-process on QA // SIT QA | 4 | 202606
2026-06-03 | applyMapping QA // Transfer new DG-rules to Prod // applyMapping Prod | 5 | 202606
2026-06-04 | BUG 990332: Missing DG-entries // Re-run SIT // Re-Run applyMapping | 6 | 202606
2026-06-05 | Check applyMapping Results Alice // new Script to extend DG-mapping-table | 4 | 202606
2026-06-08 | Stand-Up // Align Alice reg. DG-map-error // Meet Lydia // Doku DG // Align Michael reg. Doku | 5 | 202606
2026-06-09 | enviDataReview // process new SPs in Mapper // check Mapping-results Michael // Doku for DG | 4 | 202606
2026-06-10 | Stand-Up // Help Alice with RefsubID-topics // Klaus Software-Review // Process-desgin GIT | 5 | 202606
2026-06-11 | MVP for GIT: draft // Align Alice: misc topics // enviDataReview // contact Christina | 4 | 202606
2026-06-12 | Doku applyMapping with Alice + Michael // DG: new Mapping-table | 5 | 202606
2026-06-15 | Stand-Up // Meet Lydia // SW-Review Klaus: New specRef-Mapping // GIT: Process-design | 5 | 202606
2026-06-16 | enviDataReview // Finalize Klaus SW-Review // Align Alice reg. VAIUserDefTexts-Deletion | 4 | 202606
2026-06-17 | Stand-Up //GIT-integration new SSMS-version // Local-Admin | 3 | 202606
2026-06-18 | Christina-Meeting // Report 4 Christina // enviDataReview | 4 | 202606
2026-06-19
2026-06-22
2026-06-23
2026-06-24 | StandUp // Align reg. Map_SpecRef: User-Story: 973733 // new DG-Mapping-Table | 5 | 202607
2026-06-25 | GIT-Flow: End to End: Repo-Part // enviDataReview // Align Thomas + Klaus wg. Naming GIT | 4 | 202607
2026-06-26 | GIT-Flow: End to End: SSMS-Part // Confluence-Doku | 4 | 202607
2026-06-29 | StandUp // GIT-Flow: End to End: Rules-Part | 4 | 202607
2026-06-30 | enviDataReview // Meet Klaus + Thomas M. // Conflunence Doku | 5 | 202607
2026-07-01 | StandUp // GIT-Architecture // Moving spec-Ref-Rules to Prod | 3 | 202607
2026-07-02 | GIT-Architecture: SQL-Server + Developer // enviDataReview // Prep nText 2 nVarChar(MAX) | 5 | 202607
2026-07-03 | GIT-Architecture: azure DevOps // SIT: nText 2 nVARCHAR(MAX) | 3 | 202607
2026-07-06 | StandUp // Check results nText 2 nVARCHAR(MAX) // Meet Lydia // Create xls as test-docu | 5 | 202607
2026-07-07 | enviDataReview // Meet Klaus + Thomas M. // Update-App for Rules (Draft) | 4 | 202607
2026-07-08 | Stand-Up // Update-App for Rules (Prototype) // Check GIT-Install [Klaus/Alice] | 5 | 202607
2026-07-09 | Update-App for Rules (Prototype) // enviDataReview (very long) // Align Patrizia reg. SpecRef | 4 | 202607
2026-07-10 | Install GIT with Patrizia // Align Alice reg. DG // Ext. Update-App with INSERT | 3 | 202607
2026-07-13 | Meet Lidia // Extract Rules with wrong RuleSQL // Start Report wrong Rules | 4 | 202607
2026-07-14 | Wrong data declaration // Continue documenting wrong rules | 5 | 202607
2026-07-15 | Stand-Up // Check Rules with 'enviDataMasterDB' // BUG 1006911 | 3 | 202607
2026-07-16 | Bug 1006841 // enviDataReview // GIT-screenshots // Check Nugget-Task for Michael | 4 | 202607
2026-07-17 | Prep Task for Test of new BAHAIA-programs // Align Alice reg. DataType-problems | 5 | 202607
2026-07-20 | StandUp // Check Rules reg. TCG32 etc. tables // Meet Lidia // Correct TCG-Datatype to nchar | 4 | 202607
2026-07-21 | enviDataReview // Draft Update Rules-Table with File-SQL // Test: new TCG-DataType NCHAR | 5 | 202607
2026-07-22 | StandUp // Continue Docu GIT // Synchronize File-SQL with Rules-Table | 3 | 202607
2026-07-23 | Test: Synchronize rules with File-SQL // enviDataReview // Adapt ideas for improvement | 4 | 202607
2026-07-24 | Realize ideas for improvement // Align Alice reg. GIT-Docu // Draft: Transfer Corporate Core to Rules | 4 | 202607